## Capture Plan
CAPTURE MANAGEMENT PLAN
Maryland Small Business Development Center — Government Contracting Workshop Series
Opportunity Name:
Agency / Customer:
Solicitation Number:
Estimated Value:
Set-Aside Type:
NAICS Code:
Expected RFP Release:
Proposal Due Date:
Contract Type (FFP/T&M/CP):
Capture Manager:
PHASE 1: IDENTIFICATION & QUALIFICATION
# | Task | Owner | Status | Date
1 | Identify opportunity (SAM.gov, GovWin, agency forecast)
2 | Qualify opportunity against capabilities and certifications
3 | Conduct initial Go/No-Go assessment
4 | Assign Capture Manager
5 | Open capture file and begin tracking
6 | GATE 1 REVIEW — Decision to pursue
PHASE 2: PURSUIT & COMPETITIVE ANALYSIS
# | Task | Owner | Status | Date
1 | Organize capture team (identify roles per Session 2)
2 | Research customer requirements and priorities
3 | Identify and analyze competitors (incumbent, likely bidders)
4 | Develop preliminary solution approach
5 | Identify teaming partners (the 'unicorn' profile)
6 | Shape the opportunity (industry days, Q&A, white papers)
7 | Establish Price-to-Win estimate
8 | Develop win strategy and 3-4 win themes
9 | Assess risk and mitigation strategies
10 | GATE 2 REVIEW — Initial Bid Decision
PHASE 3: PRE-PROPOSAL PREPARATION
# | Task | Owner | Status | Date
1 | Assign proposal resources (writers, SMEs, reviewers)
2 | Develop annotated outline and storyboards
3 | Draft Executive Summary with win themes
4 | Begin early-stage proposal products (past perf, staffing)
5 | Finalize proposal development plan and schedule
6 | Prepare teaming agreements and subcontractor SOWs
7 | Analyze RFP (when released) — reading order: A→L→M→C→B
8 | Build Compliance Matrix (see template)
9 | Plan kick-off meeting
10 | GATE 3 REVIEW — Final Bid Decision
PHASE 4: PROPOSAL DEVELOPMENT
# | Task | Owner | Status | Date
1 | Conduct proposal kick-off meeting
2 | Submit questions to Contracting Officer
3 | Finalize compliance matrix and proposal outline
4 | Write proposal sections (features + benefits + proof)
5 | Develop original proposal graphics
6 | Conduct Pink Team review (~30-40% complete)
7 | Revise based on Pink Team feedback
8 | Complete cost volume with DCAA-compliant rates
9 | Conduct Red Team review (~80-90% complete)
10 | Revise based on Red Team feedback
11 | Final production — formatting, page counts, compliance check
12 | Conduct Gold Team review (executive sign-off)
13 | GATE 4 REVIEW — Proposal Submission
14 | Submit proposal (target: 2 days early)
PHASE 5: POST-SUBMITTAL
# | Task | Owner | Status | Date
1 | Update capture strategy for evaluation phase
2 | Respond to Evaluation Notices (ENs) if received
3 | Prepare for oral presentations (if required)
4 | Respond to Final Proposal Revision (FPR) / BAFO
5 | React to award notice (win or loss)
6 | Attend award debrief
7 | Archive proposal files and lessons learned
8 | GATE 5 REVIEW — Lessons Learned